## Sheet1
OSP Minor Work | Time Intervals/ Business Days | Notes for RTT
HDSL (SA DS1 ) - Test & Tag | 1 to 5 days if no pair conditioning is needed. Period is longer the further the customer is out. Add standard interval time after field work is done for customer date. | Test and Tag copper for service turnup
HDSL (SA DS1 ) Circuit Conditioning (HDSL w CXM) | HDSL (SA DS1 ) from the office… should be 2 to 7 days depending on the condition of the plant. Add standard interval time after field work is done for customer date. | Circuit Conditioning for services
HDSL (SA DS1 ) Doubler installation (HDSL w CXM) | Whether or not a permit is required placing a new repeater could take as little as 2-3 days to 15 or more depending on where the repeater has to be placed. We don't normally have to have a permit for housings. Add standard interval time after field work is done for customer date. | Doubler Installation for Service
Place RT Card | 1 to 5 days if card and slot is available. Add standard interval time after field work is done for customer date. | Place RT card
Add New RT Shelf - | 2 to 6 weeks if space, cooling and power will accommodate additional shelf. Add standard interval time after field work is done for customer date. | Add New Shelf to Existing RT
Re-Cable RT | Cuts… could be 5 to 45 days depending on customer notification. Customer contact is needed (Static IP's, circuits), number of customers to roll, provisioning support. 30 – 60 days to remove existing POTS shelf and place MUX or DS1 extension shelf. Add standard interval time after field work is done for customer date. | Re-Cable to rearrange existing service for new service request
Place Fiber Riser / Dark Fiber Jumper | Placement of fiber riser depends on building owner situation, conduit, right to place. If favorable this can be accomplished in 15 to 30 days. Dark fiber jumper in 1 to 5 days assuming whatever that is going to be jumpered is there. Just a matter of the type of connectors and length of jumper . If conduit is not in place, anywhere from 10-45 days, depending upon when customer places conduit. Add standard interval time after field work is done for customer date. | Fiber cable installation or fiber cable jumper required
Place NID- | 1 to 5 days. Add standard interval time after field work is done for customer date. | Place NID
Fiber Test and Tag | 3 to 15 days depending on the locations and number of fibers to be tested. Add standard interval time after field work is done for customer date. | Test and Tag fiber for service turnup
OSP Major
HDSL (SA DS1 ) w/ Construction - Copper Placing | 7 to 45 days. Depends on situation, contruction, splicing placing, municipality and permitting. Add standard interval time after field work is done for customer date. | Construction required for copper placement to turnup service
Hybrid w/ Construction | 5-30 days for construcion and splice. Insert permitting timeframes as applicable. Add standard interval time after field work is done for customer date. | Construction required for service turnup
Place New RT Mux w/ Existing Fiber | A completely new mux can take 30 to 60 days depending on space, power, cooling in the RT. If just adding cards to an existing mux, it would be 15 to 30 days. Add standard interval time after field work is done for customer date. | New RT placement, fiber cable existing
Place New RT Mux and Fiber ( < 2,500' (??) | Depends on situation depending on aerial or buried construction, placing, municipality and permitting. 30 to 75 days. Add standard interval time after field work is done for customer date. | New RT placement required with fiber cable placement
Place New RT Mux and Fiber ( > 2,500' (??) | Depends on situation, aerial or buried construction, placing, municipality and permitting. 30 to 180 days. Add standard interval time after field work is done for customer date. | New RT placement required with fiber cable over 2500 feet
Place New RT Mux w/ ROW & Structure | Depends on situation, placing, municipality and permitting. ROW can take longer to acquire. 45 to 120 days. Add standard interval time after field work is done for customer date. | New RT placement required with new ROW needed, fiber placement required
Place New Shelf and Fiber | Depends on situation and how much fiber needs to be placed, placing, municipality and permitting. If you are talking just the pigtails to the site and shelf, 1-3 weeks for installation and test and turn up. Add standard interval time after field work is done for customer date. | Place new shelf and fiber
Place Fiber Riser / Dark Fiber Jumper | 2-6 days total if the conduit is in place. (1-3 days, depending upon length to place. 1-3 days to splice, depending upon size of fiber.) If conduit is not in place, anywhere from 10-45 days, depending upon when customer places conduit. Fiber jumpers are 1 day, given we have the correct jumpers on hand. Add standard interval time after field work is done for customer date. | Place new fiber in either riser or new fiber jumper
Place NID and Fiber ( < 2,500' (??) | Depends on situation The construction of the fiber is what takes the time, placing, municipality and permitting. 30 to 75 days. Add standard interval time after field work is done for customer date. | Place new fiber cable
Place NID and Fiber ( > 2.500' (??) | Depends on situation the construction of the fiber is what takes the time, placing, municipality and permitting. 30 to 120 days. Add standard interval time after field work is done for customer date. | Place new fiber cable over 2500 feet