## 26.0 Question Log
Q # | Status | Trouble Ticketing Type | Field Name | Date Opened | Issue/Question | Date Answered | Resolution/Answer
1 | Closed | All | N/A | 2012-05-23 | When does Qwest plan to start supporting tickets in Minnesota? | 2012-06-15 | MN Commission will need to lift the order that prohibits CTL from accepting MN tickets.
2 | Closed | All | N/A | 2012-05-23 | Does Qwest plan to decommission the existing Qwest MEDIACC in the near future (and replace with MTG)? | 2012-06-15 | CenturyLink has stated its intention to retire MEDIACC consistent with processes and timeframes agreed to in connection with the Qwest/CenturyLink merger. Consistent with these agreements, MEDIACC will continue to be available to CLECs at this time, and will not be retired until at least October 2013, unless (a) MEDIACC is no longer used, and (b) CenturyLink requests and commissions approve an earlier retirement date.
3 | Closed | All | N/A | 2012-05-23 | The XSD files in section 3 of the MTG Interface specification document seem to be missing the last few lines. Can all the XSD be emailed to us? | 2012-06-15 | CTL will update MTG implementation guide with the missing XSD files.
4 | Closed | All | AuthorizationList | 2012-05-23 | Section 5.3.2 of the MTG Implementation Guidelines states "...CenturyLink supports customer authorization requests as AuthorizationList attribute or as AdditionalTroubleInfo. CenturyLink will provide a reply to authorization request in the form of AdditionalTroubleStatusInfo rather than providing AuthorizationList attribute in the AttributeValueChangeNotification". Actually, this workflow is incorrect as the Agent(CenturyLink) requests authorization and the Manager(CLEC) will provide. Can you clarify the process by which CenturyLink will request authorization? | 2012-06-15 | CTL will re-write this section of the implementation guide to accurately outline process of authorization.
5 | Closed | All | N/A | 2012-05-23 | The WSDL location was provided in Questionnaire document (note that we send a boolean sync response). Can CenturyLink add a userid and password as part of the soap header when sending a request to a CLEC web service? Below is a sample. <soapenv:Header> <wsse:Security soapenv:actor="http://schemas.xmlsoap.org/soap/actor/next" soapenv:mustUnderstand="0" xmlns:wsse="http://schemas.xmlsoap.org/ws/2002/07/secext"> <wsse:UsernameToken> <wsse:Username>UID</wsse:Username> <wsse:Password>PWD</wsse:Password> </wsse:UsernameToken> | 2012-06-15 | CLEC will need to open a change request (CR) via the CMP process. Send Questions to: CMPCR@qwest.com
6 | Closed | All | RetrieveAttributesByTroubleReportIdResponse | 2012-05-23 | The RetrieveAttributesByTroubleReportIdRequest has a RetrieveAttributes field which CLEC will send. Can CenturyLink limit the fields in RetrieveAttributesByTroubleReportIdResponse to just those fields? For example, if CLEC does not send <tML-TABase:AdditionalTroubleInfoList>true</tML-TABase:AdditionalTroubleInfoList> in the request, then CenturyLink will not include it in response. | 2012-06-15 | CLEC will need to open a change request (CR) via the CMP process. Send Questions to: CMPCR@qwest.com
7 | Closed | All | N/A | 2012-08-13 | Implementation Guidelines section 2.5.7: Customers will be assigned both a network ID and UserID during the MTG Customer Implementation process; Section 5.4: The account Name is assigned by CenturyLink during onboarding. CenturyLink requires that this value be sent by the customer for authorization. What are the values to be used? | 2012-08-31 | CTL will be providing the networkID and UserID during the implementation process.
8 | Closed | All |  | 2012-07-26 | Trouble Report format Definition 3 does not require fields such as aLocationACcessAddress/Person on the request. However it may be provided by the customer. Please confirm that will not be an issue for MTG if those fields are provided. | 2012-08-24 | Any optional fields in MTG (ref to http://www.centurylink.com/wholesale/systems/mtg.html MTG Supported Transactions Trouble Administration document). Optional fields may or may not be provided by the customer and will not be an issue if provided.
9 | Closed | All |  | 2012-07-26 | 1. AGWTA interface - requests to QWEST from our application could use QWEST WSDL and the response back from QWEST to (our application) should be based on (our application) WSDL.Is there any issue with this interface specifications? | 2012-08-24 | You will need to open a change request (CR) via the CMP process. Send Questions to: CMPCR@qwest.com
10 | Closed | All |  | 2012-07-26 | Does QWEST want to have specific fields that are not supported by other vendors (optional to other vendors but mandatory by QWEST)? What are the mandatory fields? | 2012-08-24 | Refer to MTG Implementation Guidelines http://www.centurylink.com/wholesale/downloads/2012/120806/MTG_Implementation_Guidelines_v2_080612.doc, section 5.4 Critical Attributes for Flow-Through. Also refer to section 2.4.4 tML Header in the MTG Interface Specification
11 | Closed | All |  | 2012-07-26 | What Values are supported for NetworkId | 2012-08-24 | Refer to MTG Implementation Guidelines http://www.centurylink.com/wholesale/downloads/2012/120806/MTG_Implementation_Guidelines_v2_080612.doc, section 5.4 Critical Attributes for Flow-Through. Also refer to section 2.4.4 tML Header in the MTG Interface Specification
12 | Closed | All |  | 2012-07-26 | What Values are supported for account name | 2012-08-24 | This is the ACNA associated with the CLEC. Typically 3 alpha numeric characters. No character restrictions.
13 | Closed | All |  | 2012-07-26 | What valuse are suported for NameBindingId | 2012-08-24 | String, no char restrictions. Also refer to section 5 Examples of tML-TA for Trouble Ticketing in the MTG Interface Specification
14 | Closed | All |  | 2012-07-26 | What values are supported for UserID | 2012-08-24 | These values are assigned to the CLEC by CenturyLink. values will be 1, 2 or 3 and you can refer to section 4.1 MTG Interface Specification Release 1 0 090211.doc for more details. http://www.centurylink.com/wholesale/downloads/2012/120113/MTG_Interface_Specification_Release_1_0_090211.doc
15 | Closed | All |  | 2012-07-26 | What values are used for TroubleReportFormatID | 2012-08-24 | Values will be 1, 2 or 3 and you can refer to section 4.1 MTG Interface Specification Release 1 0 090211.doc for more details. http://www.centurylink.com/wholesale/downloads/2012/120113/MTG_Interface_Specification_Release_1_0_090211.doc
16 | Closed | All |  | 2012-07-26 | What valuse are used for ServiceProfile? | 2012-08-24 | String, no char restrictions. Valid Value should be ‘RESELLER’ or ‘WHOLESALE’.
17 | Closed | All |  | 2012-07-26 | What would be the optimum respons time for create and update transactions? | 2012-08-24 | Response times experienced today in CEMR/MEDIACC will be equal to or better in CEMR/MTG and MTG at this time.
18 | Closed | Late bonding |  | 2012-07-26 | 5. Late e-bond - how does it work? What response is sent back to us? How does the ticket gets late e-bonded to QWEST? Would there be any changes in the new interface? | 2012-08-24 | Refer to section 7.2.2 Manual to Electronic Recovery – Late Bonding under Implementation guideline http://www.centurylink.com/wholesale/downloads/2012/120113/MTG_Implementation_Guidelines_v1.pdf
19 | Closed | All |  | 2012-07-26 | 6. What URL needs to be used by <CLEC> to interface with QWEST? How does QWEST authenticate the requests transactions from <CLEC>? The authentication process needs to be discussed. | 2012-08-24 | CTL will provide the URL during implementation. Authentication requirements can be found in section 4 of the Implementation Guidelines document.
20 | Closed | POTS |  | 2012-07-26 | 7. Does New POTS Test Request Types been used for MLT transaction? Do CLT support MLT in Gateway initiated transaction? | 2012-08-24 | Yes, we support MLT. Refer to section 3. MTG Ticketing System XSD Usage under CTL specification document. http://www.centurylink.com/wholesale/downloads/2012/120113/MTG_Interface_Specification_Release_1_0_090211.doc
21 | Closed | All |  | 2012-07-26 | 8. MTG has restrictions on TroubleTypeValueType. What valid values will be expected by CTL? | 2012-08-24 | Refer to APPENDIX J, APPENDIX M and APPENDIX P http://www.centurylink.com/wholesale/downloads/2012/120113/MTG_Implementation_Guidelines_v1.pdf
22 | Closed | All |  | 2012-07-26 | 9. What are the different notification operations for AVCNs and Async Responses? | 2012-08-24 | MTG uses one operation for both AVCNs and Async Responses.
23 | Closed | All |  | 2012-07-26 | 10. To support flash cut migration, what are the impacts on QWEST to support updates on the existing open tickets which were previously e-bonded to QWEST via ECTA or ECTA-CRM?. | 2012-08-24 | You should use MTG for all your new tickets and you will continue to use MEDIACC until all of your existing MEDIACC tickets are closed.
24 | Closed | All |  | 2012-10-19 | We have been reviewing the MTG Specs and had a question – When we send MTG a ModifyAttributesRequest, MTG will send us a tml-OK/SOAP fault synchronously and a ModifyAttributesResponse asynchronously. Will the CorrelationID on the ModifyAttributesResponse be the same as the CorrelationID on the ModifyAttributesRequest? If not, what field on the XML can be used to match the ModifyAttributesResponse to the corresponding ModifyAttributesRequest? (as there could be multiple ModifyAttributesRequests for the same ticket and all would have the same track id). | 2012-10-23 | Both CorrelationID and TrackID is unique and persistent for the life of the ticket. CorrelationID on the ModifyAttributesResponse should be same as the CorrelationID on the ModifyAttributesRequest.
25 | Closed | Pots |  | 2012-10-24 | Can you please clarify if the POTS Uncontrolled Test Response asynchronous or synchronous? As per section 1.5 in the MTG specs, it looks like RequestTroubleReportCreation, ModifyAttributes, CancelTroubleReport, RetrieveAttributesbyTroubleReportID responses are asynchronous but we did not find a flow diagram for POTS Uncontrolled Test so wanted to confirm. | 2012-10-24 | It is Asynchronous.
26 | Closed | all |  | 2012-11-26 | <A CLEC> asks that CenturyLink modify its acceptance of digital certificates to reflect the following: When <the CLEC> sends transaction to CTL, <the CLEC> will attach the <CLEC’s> certificate to that transaction for authentication. When CTL sends transaction to <the CLEC>, CTL will attach CTL certificate to that transaction for authentication. | 2012-11-30 | CenturyLink will try <the CLEC>’s request on a pilot/test basis. If the test proves successful, a CMP CR will be issued to open this option up to other customers and CenturyLink will update its documentation accordingly. The new option will provide the ability to process transactions with the digital certificate configuration specified in the pilot/test (inbound to CenturyLink using <the CLEC>’s digital certificate, outbound to <the CLEC> using CenturyLink’s digital certificate). Both the currently documented option as well as this new option would be available to all CLEC customers if testing is successful and the new option is implemented for <the CLEC>.
27 | Closed | All |  | 2012-12-10 | CenturyLink (Legacy Qwest) sends an outbound message to us via SSL and AT&T receives that message. CTL then keeps that connection open for subsequent messages. This is how they manage with all the companies they work with. AT&T, conversely, severs connections after every transaction. AT&T views this as an essential security measure, and has this same process with over 200 of the companies they work with. At this time AT&T is not researching an option to change this security practice. AT&T requests CenturyLink to also sever the connection after every transaction. This is compliant with AT&T’s security practice. | 2012-12-14 | Please open a CMP CR for this effort and we will continue to explore options and possible solutions to accommodate AT&T’s request for transaction termination
28 | Closed | All | n/a | 2012-12-10 | During testing we found out that the response Qwest sends has CDATA. But, our current code does not support this. We were expecting that the response will follow HTML encoded format similar to the request sent CTL. We will need a lot of code changes from our end to support this CDATA. Dev team is still analyzing on the effort and feasibility. Instead, Can Qwest send the response (notification also) in HTML encoded format, similar to request that Qwest receives? Please advise. | 2012-12-14 | CLEC will need to open a change request (CR) via the CMP process. Send Questions to: CMPCR@qwest.com
29 | Closed | All | n/a | 2013-01-21 | (CLEC) follows the 2 level security check to determine the requests sent to the web service are from trusted source. We can configure the gateway to verify following in the ws – security header of the SOAP request send by the client. 1) The username /password in the ws security header. The username and password are provided by Verizon for test and production environments and they will be included in the header of all SOAP requests sent to the web service. 2) A digital signature of the content of the message. A private /public key pair(X.509 certifcare) will be generated . The client uses the private key to digitally sign the content of the message and the public key will be installed on the Verizon side to verify the signature. We would ask CTL to implement digital signature. | 2013-01-23 | CLEC will need to open a change request (CR) via the CMP process. Send Questions to: CMPCR@qwest.com
30 | Closed | Create | TRACKID | 2013-01-07 | From (our) perspective the issue for us is that currently Qwest will not accept the same track id even if a trouble report is not created. Specifically on a create request if the transaction fails for any reason and we attempt to resubmit the same transaction with the same trouble report id we are receiving a reject for “Duplicate TrackId”. As TrackId is a new field required by us we do not face such an issue in Production today. The addition of the TrackId logic from the backend was a major code impact and as such we cannot implement a viable solution within the constraints of the current project timeline. The problem this presents as it stands today is that any time our end users encounter this scenario in Production they will not be able to simply resubmit a transaction in the application. They will need to duplicate the entire process of reentering the information and creating a new request which will result in increased handle time. | 2013-01-08 | CLEC will need to open a change request (CR) via the CMP process. Send Questions to: CMPCR@qwest.com
31 | Closed | n/a | n/a | 2013-01-08 | Requesting Late Ebonding for POTS and escalations for POTS. Functionality does not currently exist in MEDIACC today, requesting for MTG. | 2013-01-08 | CLEC will need to open a change request (CR) via the CMP process. Send Questions to: CMPCR@qwest.com
32 | Closed | all | n/a |  | Can you can send us security header in the soap header section of the Ta response and AVC TML. | 2013-01-14 | CLEC will need to open a change request (CR) via the CMP process. Send Questions to: CMPCR@qwest.com
33 | Closed | RetrieveTroubleReportId | n/a | 2013-01-02 | In the Tech Spec section 5.7, there is a sample for RetrieveAttributesByTroubleReportIdRequest but the transaction we are referring to is RetrieveTroubleReportStatusRequest. This is a different transaction which will return a response of the most current status – it is currently supported in the CMIP flow but we could not find a reference to it in the XML flow to MTG. Can you please clarify if it is supported by Qwest MTG? | 2013-01-14 | We do support this! RetrieveAttributesByTroubleReportId can be used to retrieve the most current status, ticket status and also other attributes related to the ticket. Please find the reference from Tech spec and Implementation guide – In Tech spec – refer to Section 5.7 RetrieveAttributesByTroubleReportIdRequest, page 33. And in Implementation guide – refer to Section 5.1.2 Retrieve Trouble Report (RetrieveAttributesByTroubleReportIdRequest) 19, page 19.